## Sheet1
Modules and Contents for Task
| No | Modules | Contents | Estimated Time
| 1 | Graphic Design & UI design for Site | Make MockUp for site ( 3 pages - Index, SDK Documantation, Walkthrough ) | 3 days
|  |  | Logo Design ( Logo for Website by using Photoshop ) | 1 day
|  |  | Design of icons and other images ( file format : png ) | 2 days
|  |  | Original design of site with Photoshop | 2 days
| 2 | Wesite Design based on graphic design | Web site design ( 3 pages - Index, SDK Documentation, Walkthrough ) with HTML, CSS, JavaScript : Index page - 2 days, SDK Documentation - 1 day, Walkthrough - 2 days | 5 days
| 3 | Coding for Chat program, Data entry for Documentation, Coding Walkthrough | Coding in index page for chat by using PubNub | 10 days
|  |  | Enter all information for SDK Documentation | 2 days
|  |  | Coding Walkthrough with PHP, HTML, CSS, JavaScript | 2 days
| 4 | Test program | Test with each module & Integrate Test | 3 days
|  | Finalize | Upload on GitHub and Final Test | 1 day
| Total Days |  |  | 31 days
※ This schedule and modules are made based on orginal requirements. It will be updated and exchanged with client.

## Sheet2
Schedule of PubChat with PubNub
[11 empty] | September | [5 empty] | October | [8 empty] | October | [9 empty] | October | [8 empty] | October
Step | SubStep | Work Content | Foresight |  |  | Fact
|  |  | Start | Days | Last | Start | Days | Last | Delay | Advance | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Step-1 | 1 | Requirements Analysis & Design of Schedule and Basic Content | 2013-09-25 | 6 | 2013-09-30 | 2013-09-25 | 6 | 2013-09-30 |  | •
| 1_1 | Discuss task in details with client | 2013-09-25 | 1 | 2013-09-25 | 2013-09-25 | 1 | 2013-09-25 |  | •
| 1_2 | Research about PubNub and PubChat with it | 2013-09-26 | 2 | 2013-09-27 | 2013-09-26 | 2 | 2013-09-27 |  | •
| 1_3 | Scheduling Work | 2013-09-28 | 1 | 2013-09-28 | 2013-09-28 | 1 | 2013-09-28 |  | •
| 1_4 | Desgin of task (Module, Content, etc) | 2013-09-29 | 2 | 2013-09-30 | 2013-09-29 | 2 | 2013-09-30 |  | •
Step-2 | 2 | Graphic Design & UI design for Site | 2013-10-01 | 13 | 2013-10-13 | 2013-10-01 | 13 | 2013-10-13
| 2_1 | Make MockUp for site | 2013-10-01 | 3 | 2013-10-03 | 2013-10-01 | 3 | 2013-10-03 |  | •
| 2_2 | Graphic Design | 2013-10-04 | 5 | 2013-10-08 | 2013-10-04 | 5 | 2013-10-08 |  | •
|  | 2_2_1 Logo Design | 2013-10-04 | 1 | 2013-10-04 | 2013-10-04 | 1 | 2013-10-04 |  | •
|  | 2_2_2 Icon & Visual UI Design | 2013-10-05 | 2 | 2013-10-06 | 2013-10-05 | 2 | 2013-10-06 |  | •
|  | 2_2_3 Site UI Design | 2013-10-07 | 2 | 2013-10-08 | 2013-10-07 | 2 | 2013-10-08 |  | •
| 2_3 | Web Design based on MockUp and Graphic Design | 2013-10-09 | 5 | 2013-10-13 | 2013-10-09 | 5 | 2013-10-13 |  | •
Step-3 | 3 | Realize Logic, Documentation and Workthrough | 2013-10-14 | 14 | 2013-10-27 | 2013-10-14
| 3_1 | Realize Logic and Coding | 2013-10-14 | 10 | 2013-10-23 | 2013-10-14
| 3_2 | Documantation | 2013-10-24 | 2 | 2013-10-25
| 3_3 | Workthrough | 2013-10-26 | 2 | 2013-10-27
Step-4 | 4 | Test and Finalize | 2013-10-28 | 4 | 2013-10-31
| 4_1 | Unit Test | 2013-10-28 | 2 | 2013-10-29
| 4_2 | Integrate Test | 2013-10-30 | 1 | 2013-10-30
| 4_3 | Finalize | 2013-10-31 | 1 | 2013-10-31